## Slide 1: Heal, Rise, Live…Repeat A Journey to Trauma-Informed Care
Implementing Trauma-Informed Care (TIC) and Approaches with Montana Indian Health Care Organizations
Indian Health Services Billings Area Office & Mountain-Pacific Quality Health
Status Report
March 28, 2019

## Slide 2: Meet the Team
Katelin Conway Project Manager
Main point of contact
Alona Jarmin Clinical Support
Provide guidance on policies
Amanda Eby Project Support
General project support
Project tracking
Meeting planning and facilitating
Project reports
Coordinate subject matter experts (SME)
Staff training
Assist with materials
Research

## Slide 3: Grant Overview
Year 1/Quarter 1
Governance & Leadership
Policy
Year 1/Quarter 2
Physical Environment
Patient/Tribal Member Involvement
Year 1/Quarter 3
Cross Sector Collaboration
Year 1/Quarter 4
Training and Workforce Development
Introduction
Leadership Buy-In.
Create workgroup
Develop and implement trauma-informed care policies
Assess environment to be inviting and supportive
Create shared areas that welcome cultural healing methods
Engage patients/tribal members in planning process
Facilitate incorporating patient feedback
Foster partnerships that support a trauma-informed approach & encourage traditional healing
Train staff on policies/procedures, trauma-screening tools and referral processes, de-escalation, follow-up and support.
Facilitate communication with partners about goals and priorities for trauma-informed care
Assist with developing policies to support staff with historical or secondary trauma
Year 2
Screening, Assessment and Treatment Services
Progress Monitoring and Quality Assurance
Assess organization’s ability to provide trauma-specific treatment
Assess implementation progress and identify strengths and weaknesses
Guide monitoring
Assist with selecting trauma screening tool(s) & develop workflow for implementation
Support human resources (HR) to incorporate TIC principles into hiring, supervision and evaluation
Notes: Year one of the project will focus on laying the groundwork for transforming organizations to trauma-informed cultures. Mountain-Pacific’s mission will be to meet the needs of the tribal members, recognizing that there’s no universal definition of trauma and each service unit’s model for trauma-informed care will be tailored according to the tribe’s culture. We will incorporate tribal healing methods, the SAMHSA Concept of Trauma and Guidance for a Trauma-Informed Approach and the Center on Health Care Strategies’ Advancing Trauma-Informed Care Initiative, funded by the Robert Wood Johnson Foundation.
Year two of the projects will transition the governance structure and training groundwork into action. Mountain-Pacific staff will work with Indian health organizations to test and implement tools for screening for trauma and design and monitor workflows for training. We will support staff with trauma treatment and referral processes adapted to the organization’s resources and monitor and offer feedback on weaknesses and strengths of trauma-related workflows.

## Slide 4: Workplan
Tasks | Current Progress | Due Date
1. Create standardized policies and procedures within each organization for trauma-informed approaches. | Researched templates Met with South Central Foundation (SCF) Ready to create workgroup to develop draft(s) | March 31, 2019
2. Design emotionally safe environments within organizations and involve trauma survivors/patients in the planning process | Site visits with Riverstone & St. Vincent Developing checklist for sites | June 30, 2019
3. Engage partners across the health care sector and community-based organizations in trauma-informed approaches | Kickoff Meeting February 2019 Leadership Meeting w/ Service Units March 2019 Need to connect with Tribal and some of the Urban Programs Determine next steps with each facility, driven by BAO guidance | September 30, 2019
4. Train clinical and non-clinical staff on trauma-informed principles, policies and procedures, trauma screening tools and treatment options or referral processes | Introductory training provided by Riverstone Health to CEOs and leadership team Need to determine training options (ie. Train the trainer) | December 31, 2019
5. Implement and test selected screening tools with workflows designed to allow for flexibility to incorporate traditional cultural healing methods | - Not started | Starting in January 2020 and continuing through the year.
6. Guide ongoing monitoring, tracking and evaluation of the implementation of trauma-informed principles; progress of tribe-specific goals; effectiveness of trauma screening tools, treatment and rates of referral follow-up | - Not started | Starting in January 2020 and continuing through the year.

## Slide 5: Outcomes
Each IHS service unit, tribal health department and urban center will have trauma-informed policies and procedures in place, including staff training materials and guides for trauma screening, treatment or referral.
Indian health organizations’ clinical and nonclinical staff will receive training on the impact of trauma, recognize the symptoms and understand how to appropriately respond.
Indian cultural healing methods are accepted and encouraged as tools to building resiliency and recovering from trauma.

## Slide 6: Discussion
Define metrics to measure progress
  How do you want to measure your success in meeting the project outcomes?
    Policy and procedure checklists for each organization
    Assess staff to measure their understanding of trauma, ability to recognize symptoms and confidence in responding to trauma
    Assess medical providers’ comfort level in prescribing/encouraging Indian cultural healing methods for recovering from trauma
    Assess patients/tribal members’ use of cultural healing methods to cope and heal from trauma
Expectations of Mountain-Pacific
  Clearly defined roles and responsibilities

## Slide 7: Discussion
Expectations of Mountain-Pacific
  Clearly defined roles and responsibilities
  How can we best support you?
  Are there other experts you want to hear from?
  Are there resources you like more than others for us to use?
  How often do you want to meet?
    Virtually
    In-person

## Slide 8: Moving Forward
Heal, Rise, Live…Repeat Website
  https://www.mpqhf.org/QIO/trauma-informed-care-grant-project-home/
Learning Action Network (LAN) Model
  Quarterly presentations
  Monthly Check-in

## Slide 9: Questions?
Katelin Conway, MBA, MPH
406-422-3169
kconway@mpqhf.org
Alona Jarmin, RN, BSN, MSN
406-594-0217
ajarmin@mpqhf.org
Amanda Eby
406-457-5846
aeby@mpqhf.org
WE ARE HERE TO SUPPORT YOU IN YOUR JOURNEY!